## Sheet1
CPE 481 Schedule of deliverables
Month
September | 9 to 16 | Orientation and Groupings
September | 16 to 23 | Pitching of Projects Individual | See Abstract Examples from researchgate or google scholar
September | 23 | Approval of proposals and official groupings (ABSTRACT) | see Approval Sheet
September | 30 | Project consulation with Advisers (Adviser Hunt) | can be any adviser from CPE and or Instructors with CPE undergrad and Masters Degree
October | 1 to 7 | Introduction Document Check (Why, What, How) Include Statistical data for the need of this project Based on reputable Fact. | See Documentation Proposal Template (fill out section 1.1 Problem Background, 1.2 Project Goal and Objectives, 1.3: Significance of the Study)
October | 8 to 14 | Consult with your Adviser/s on progess of Work. | See Project Design Consultation Monitoring Template. Have the adviser sign the Design Consultation Monitoring Template
October | 15 to 21 | Research on Review of Related Lit. () Include Facts showing similarities and differences of your project vs theirs (@ least 3) | See Documentation Proposal Template (Fill out section 1.4 Theoretical Background, 1.5 RRL 1.6 definition of terms)
October | 21 to 28 | Consult with your Adviser/s on progess of Work and ask for Method suggestions | See Project Design Consultation Monitoring Template. Have the adviser sign the Design Consultation Monitoring Template
October | 29 to November 11 | Research Methodology Show market Research on needs, and the DETAILED Technologies used for your project) | As per approval of your adviser/s See Documentation Proposal Template (Fill out section 2.1 block Diagram, 2.2 Project management, 2.3 Prototype design, 2.4 Circuit design, 2.5 Program Flowchart)
October | 29 to November 11 | Consult with your Adviser/s on progess of work and ask for Method suggestions/ Design Changes and or addition or removal. | See Project Design Consultation Monitoring Template. Have the adviser sign the Design Consultation Monitoring Template must be signed weekly
November | 11 to 25 | Test Methods for your Methods. (Must be scientific test that validates performance of either unit and or integration) ex https://stattrek.com/ | As per approval of your adviser/s See Documentation Proposal Template (Fill out section 2.6 Testing and Data Gathering and FULL reference)
November | 11 to 25 | Consult with your Adviser/s on progess of work and ask for Method suggestions/ Design Changes and or addition or removal. | See Project Design Consultation Monitoring Template. Have the adviser sign the Design Consultation Monitoring Template must be signed weekly
November | 25 to December 2 | Creation of Kickstarter Video
December | 2 to 9 | Proposal Presentation | Fill out Requiement specifications Based on Approved Documentation Proposal Template see requirement specs template