## Sheet1
Telemetry
Group Name | [5 empty] | Project Start: | 2023-12-05
[6 empty] | Display Week: | 1 | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25
[8 empty] | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31
TASK | ASSIGNED TO | STATUS | PROGRESS | NOTES | START | DAYS | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Class Orientations |  |  |  |  | 2023-09-09 |  | 2023-12-16
Class Orientation I |  | Completed | 100% | Meeting Link: https://cebuinstituteoftechnology.sharepoint.com/:v:/s/CpE481H1-H2Sem12022-2023480/ERiXdSUK0GJKl64OerYmgnMBbk4v4KcuAW-VzLxu17UIiQ?e=GA0As4&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZyIsInJlZmVycmFsQXBwUGxhdGZvcm0iOiJXZWIiLCJyZWZlcnJhbE1vZGUiOiJ2aWV3In19 | 2023-09-09 | 1 | 2023-09-09
Class Orientation II |  | Completed | 0% | Pitching of Projects Individual | 2023-09-16 | 1 | 2023-09-16
Class Orientation III |  | Completed | 0% | Approval of proposals and official groupings (ABSTRACT) | 2023-09-23 | 1 | 2023-09-23
Class Orientation IV |  | Completed | 0% | Project consulation with Advisers (Adviser Hunt) | 2023-09-30 | 1 | 2023-09-30
Presentation Week |  | In Progress | 0% | Project consulation with Advisers (Adviser Hunt) | 2023-12-11 | 6 | 2023-12-16
Ideas |  |  |  |  | 2023-09-09 |  | 2023-09-15
Project Proposal | Aricayos | Completed | 0% | https://www.aises.org/sites/default/files/documents/National%20Conference/Abstract%20Guidelines%20and%20Samples.pdf | 2023-09-09 |  | 2023-09-08
Project Proposal | Cabansay | Completed | 0% |  | 2023-09-09 | 7 | 2023-09-15
Project Proposal | Pol | Completed | 0% |  | 2023-09-09 | 7 | 2023-09-15
Finding Advisor | Team | Completed |  |  | 2023-09-09 | 22 | 2023-09-30
Deliverables |  |  |  |  | 2023-09-04 |  | 2023-09-06
Github Repository | Aricayos | Completed | 100% | Link: https://github.com/razstvien01/cpe_practice_design
Project Design Proposal |  | Not Started | 5% |  | 2023-09-04 | 1 | 2023-09-04
Approval Sheet |  | Not Started | 6% |  | 2023-09-05 | 1 | 2023-09-05
Project Requirement Specifications |  | Not Started | 0% |  | 2023-09-06 | 1 | 2023-09-06
Chapter 1 |  | Not Started | 0% |  | 2023-12-11 | 6 | 2023-12-16
Chapter 2 |  | Not Started | 0% |  | 2023-12-11 | 6 | 2023-12-16
Kickstarter Video |  | Not Started | 0% |  | 2023-12-11 | 6 | 2023-12-16
Designs |  |  |  |  | 2023-12-07 |  | 2023-12-16
Circuit Diagram (Chapter 2) | Cabansay | Not Started | 5% |  | 2023-12-07 | 10 | 2023-12-16
Entity Relationship Diagram | Aricayos | Not Started | 6% |  | 2023-12-07 | 10 | 2023-12-16
Data Flow Diagram |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Block Diagram (Chapter 2) |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Program Flowchart | Aricayos | Not Started | 3% |  | 2023-12-07 | 10 | 2023-12-16
Chapter 1 |  |  |  |  | 2023-12-07 |  | 2023-12-16
Problem Background |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Project Goal and Objectives |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Significance of the Study |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Theoretical Background |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
RRL |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Definition of Terms |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Chapter 2 |  |  |  |  | 2023-12-07 |  | 2023-12-16
Block Diagram |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Project Management Plan |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Prototype Design |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Circuit Design |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16
Testing and Data Gathering |  | Not Started | 0% |  | 2023-12-07 | 10 | 2023-12-16